## GANTT 2021
GANTT S1 |  | Durées | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
|  |  | 20/09-26/09 | 27/09-03/10 | 04/10-10/10 | 11/10-17/10 | 18/10-24/10 | 25/10-31/10 | 01/11-07/11 | 08/11-14/11 | 15/11-21/11 | 22/11-28/11 | 29/11-05/12 | 06/12-12/12 | 13/12-19/12 | 20/12-26/12 | 27/12-02/01
Infos partiels |  | NA | S43: Exam 28/10; S44: TOUSSAINT; S45: Exam 8/11; S46: Exam 19/11; S51: NOEL; S52: NOEL
Infos livrables |  |  | S45: L1 : 9 Novembre
A | Read the given documents about plastic and machines | 2 | bar: S38 to S39
B | Meet the client, Germain LEMASSON | 1 | bar: S38
C | Meet the physiotherapist | 1 | bar: S39
D | Specifications and architectures | 2 | bar: S39 to S40
E | Make the requierments chart (one group) | 1 | bar: S40
F | To make the engine works | 3 | bar: S38 to S40
G | Organise the collect of the plastic with the RAFU network | 3 | bar: S41 to S43
H | To study the engine characteristics and see if we have to change it + Find a new one if necessary | 3 | bar: S41 to S43
I | To securise the shredder with a hopper and a cover | 3 | bar: S40 to S42
J | To install emergency button, external potentiometer and forward/backward switch | 2 | bar: S41 to S43
K | Make some tests with Germain Lemasson | 1 | bar: S50
L | Realise the housing (carter) | 2 | bar: S43; S45
M | Make the engine support | 3 | bar: S46 to S48
N | Design a bin (bac) for the big ships of plastic | 1 | bar: S49
O | Make the bin | 1 | bar: S50
P | Make final tests | 1 | bar: S50
Q | Write all document about the shredder (safety rules, working, ...) | 2 | bar: S43; S49 to S50
R | Write the deliverable n°1 | 1 | bar: S43
Ressources ?
Colors ?
Trémi+capeau pour le 19 octobre

## GANTT 2022
| S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19
| 03/01-07/01 | 10/01-14/01 | 17/01-21/01 | 24/01-28/01 | 31/01-04/02 | 07/02-11/02 | 14/02-18/02 | 21/02-25/02 | 28/02-06/03 | 07/03-13/03 | 14/03-20/03 | 21/03-27/03 | 28/03-03/04 | 04/04-10/04 | 11/04-17/04 | 18/04-24/05 | 25/04-29/05 | 02/05-06/05 | 09/05-13/05
Infos partiels | S8: HIVER; S16: VACANCES
Infos livrables | S3: L2 : 18 Janvier; S11: L3 : 15 Mars; S15: L4 : mid may; S17: L5 : end may
E | S3: PARTIELS S1
F
G
H
I
J
K
L
M
N
E | S1: Developping group for plastic plate machine
F | S1: Study the actual machine
G | S1: Study ameliorations & CAO prototype
H | S1: Fabrication
I | S1: Test and adjustments

## A
Write your name below the document you are about to read
1- documentation technique | 2- precious plastique | 3- broyeur | 4- Compression | 5- Physiotherapist
Margaux | Tom&Louis | William | Louis | Willie