## Gantt
GANTT REV.2 |  | Durées | Ressources | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19
Open source plastic recycling machine |  |  |  | 20/09 - 26/09 | 27/09 - 03/10 | 04/10 - 10/10 | 11/10 - 17/10 | 18/10 - 24/10 | 25/10 - 31/10 | 01/11 - 07/11 | 08/11 - 14/11 | 15/11 - 21/11 | 22/11 - 28/11 | 29/11 - 05/12 | 06/12 - 12/12 | 13/12 - 19/12 | 20/12 - 26/12 | 27/12 - 02/01 | 03/01 - 07/01 | 10/01 - 14/01 | 17/01 - 21/01 | 24/01 - 28/01 | 31/01 - 04/02 | 07/02 - 11/02 | 14/02 - 18/02 | 21/02 - 25/02 | 28/02 - 06/03 | 07/03 - 13/03 | 14/03 - 20/03 | 21/03 - 27/03 | 28/03 - 03/04 | 04/04 - 10/04 | 11/04 - 17/04 | 18/04 - 24/05 | 25/04 - 29/05 | 02/05 - 06/05 | 09/05 - 13/05
Exam |  | NA | NA | S43: Exam 28/10; S44: TOUSSAINT; S45: Exam 8/11; S46: Exam 19/11; S51: NOEL; S52: NOEL; S8: HIVER; S16: PAQUES
Deliverable |  |  |  | S46: L1 : 16 Novembre; S3: L2 : 18 Janvier; S11: L3 : 15 Mars; S15: L4 : mid may; S17: L5 : end may
A | Reading of technical documents | 2 | Team | S3: PARTIELS S1
B | Meeting with Germain LEMASSON | 5 | Team | bar: S38; S47; S6; S12; S19
C | Meeting with the physiotherapist | 3 | Team | bar: S39; S12; S19
D | Project management | 3 | TB/ML | bar: S38 to S40
E | Systems Engineering | 8 | LG/MC/ML | bar: S39 to S43; S45; S1 to S2
F | Connecting the converter | 2 | ML/MC | bar: S39 to S40
G | Organisation of the collect/routing of plastic | 9 | Willie/ML | bar: S41 to S43; S45 to S50
H | Study of the current engine and the engines available | 3 | MC/ML | bar: S41 to S43
I | Improvement of the shredder | 10 | TB/WL | bar: S40 to S43; S45 to S50; S1 to S2
J | Tests | 4 | Team | bar: S50; S1 to S2; S14 to S15
K | Write all open source document (safety rules, working, ...) | 13 | Willie/ML/MC | bar: S43; S50; S1 to S2; S4 to S7; S9 to S15
L | Write the deliverables | 8 | ML/MC | bar: S43; S45; S1 to S2; S9 to S10; S13 to S14
M | Press research phase | 7 | LG/MC | bar: S43; S45 to S50
N | Improvement of the press | 13 | TB/WL/LG | bar: S1 to S2; S4 to S7; S9 to S15
O | Calculation of costs | 6 | LG | bar: S41 to S42; S50; S1 to S2; S14
Code couleur
Late
In time
Advance
Past

## A
A- Reading of technical documents |  |  | Not started
In progress
Achieve
Tâche A.1 | Technical documentation
| - "Les différents types de plastique" | Link to return to the Gantt : | Gantt
- "Injection"
- "Guide pratique pour incorporer les matières plastiques recyclées"
- "Conception des pièces en plastique pour éviter les défauts géométriques"
Tâche A.2 | Documentation about the shredder
- "Motoréducteur Vassal"
- "Huike Heynau"
- "Condensateur motoréducteur"
- "Amélioration broyeur"
Tâche A.3 | Documentation about the compression of plastic
- "Test four V1"
- "Test four V2"
- "Amélioratioin compression"

## B
B- Meeting with Germain LEMASSON |  |  | Not started
In progress
Achieve
Tâche B.1 | First meeting with Mr LEMASSON (22/09/2021)
| - Presentation of himself and of the Fabmstic | Link to return to the Gantt : | Gantt
- Prensentation of the professional recycling tools
- His expectations
Tâche B.2 | Second meeting with Mr LEMASSON
- Show him our first progress
- To make clear the aim
- Speak about the communication tool
- Show him our objectives for the next few weeks
- Set a week for the next meeting
Tâche B.3 | Third meeting with Mr LEMASSON

## C
C- Meeting with the physiotherapist |  |  | Not started
In progress
Achieve
Tâche C.1 | First meeting with Manuel FRANCOIS (28/09/2021)
| - Presentation of himself/his work/his office | Link to return to the Gantt : | Gantt
- Presentation of the technique used to make thermoformable plastic splints
- His expectations
- Talk about the opportunities with the grenoble CHU
Tâche C.2 | Second meeting with Manuel FRANCOIS

## D
D- Project management |  |  | Not started
In progress
Achieve
Tâche D.1 | Make the project gantt chart
Tâche D.2 | Make the project risk analysis | Link to return to the Gantt : | Gantt

## E
E- Systems Engineering |  |  | Not started
In progress
Achieve
SHREDDER
Tâche E.1 | Define the stakeholders | Link to return to the Gantt : | Gantt
Tâche E.2 | Define the services
Tâche E.3 | Define the logical architecture
Tâche E.4 | Make the requirements chart
Tâche E.5 | Put it on capella
PRESS
Tâche E.6 | Define the stakeholders
Tâche E.7 | Define the services
Tâche E.8 | Define the logical architecture
Tâche E.9 | Make the requirements chart
Tâche E.10 | Put it on capella

## F
F- Connecting the converter |  |  | Not started
In progress
Achieve
Tâche F.1 | Read the instruction manual of the converter
Tâche F.2 | To do the wirering | Link to return to the Gantt : | Gantt
Tâche F.3 | To test the motor in a basic case
Tâche F.4 | To solder the new buttons
Tâche F.5 | To set the converter to the correct configuration

## G
G- Organisation of the collect/routing of plastic |  |  | Not started
In progress
Achieve
Tâche G.1 | To organise the collect of ABS plastic in GI | Notes :
- To make a clear laminated notice showing the carton below and saying to throw away unused parts
| - To install a bin to replace the carton in which the ABS unused parts are thrown away | We asked to Jean-François. A big bin of Ginova will be change soon. So we will take it at this moment
Tâche G.2 | To organise the collect of plastic with the RAFU network | Notes :
| - To contact Germain LEMASSON to ask him his vision of things | Meeting : 24th of November
| - To develop a computer tool for routing plastic copings between GI and FabMSTIC | Thanks to a google sheets
Tâche G.3 | To prepare the storage of [ABS/PLA/falling plastic sheet from the physiotherapist] ships | Notes :
- To enquire about the storage of different types of plastic
| - To install differents bins to store the different type of plastic | It will not be necessary --> 'flux tendu' ; it should not have a dead center
- To determine a container for the transit of plastic ships

## H
H- Study of the current engine and the engines available |  |  | Not started
In progress
Achieve
Tâche H.1 | To calculate their torque
Tâche H.2 | To find others useful unformations | Link to return to the Gantt : | Gantt
Tâche H.3 | To make a comparative document
Tâche H.4 | To choose the most suitable engine

## I
I- Improvement of the shredder |  |  |  | Not started
In progress
|  | Notes : |  | Achieve
Tâche I.1 | To securise the shredder with a hopper
Tâche I.2 | To install a cover | hinges in print ; wrist ? | Link to return to the Gantt : | Gantt
Tâche I.3 | To install the electric part | 3D part to be made for the disjoncter ; connections to be made ; rail to be installated
Tâche I.4 | To realise the housing (carter) | Draw in progress ; material : steel
Tâche I.5 | To make the engine support
Tâche I.6 | To design a bin (bac) for the big ships of plastic | Prochaine étape --> Découpeuse jet d'eau d'E3
Tâche I.7 | To make the bin

## J
J- Final tests |  |  | Not started
In progress
Achieve
Tâche J.1 | To test the shredder by shredding ABS/PLA/Physiotherapist plastic
Tâche J.2 | To contact la casemate in order to find a press and make test and do not wait until our press is ready | Link to return to the Gantt : | Gantt
Tâche J.3 | To make test in the Casemate
Tâche J.4 | To test the compressor by making new plastic plate with the unuse plastic of the physiotherapist
Tâche J.5 | To test the compressor by making new object with PLA/ABS/PET ships
Contact pour la Casemate : Yoanna Nowicki
yoanna.nowicki@ccsti-grenoble.org

## K
K- Write all document (safety rules, working, ...) |  |  | Not started
In progress
Achieve
SHREDDER
Tâche K.1 | To write the safety rules of the shredder | Link to return to the Gantt : | Gantt
Tâche K.2 | To write a document about how to use the shredder
PRESS
Tâche K.3 | To write the safety rules of the compressor | Link given by Mr Boujut concerning open source document :
Tâche K.4 | To write a document about how to use the compressor | https://github.com/OPEN-NEXT/wp2.3_Guideline-for-documentation-of-OSH-design-reuse
Tâche K.5 | Think about which documents will be open source and write them
- Dimensional calculations
- Drawings et CAD
- Assembly advice
- Wiring diagram
- Materials used
- Security documents
- Costs
Tâche K.6 | Open and set a git GitHub
Tâche K.7 | Write the thocumentation fofowing the Open source guidelines
Introduction
Specification
Design
Manufacturing
Assembly
Use
Maintenance
Disposal
Tâche K.8 | Find a licence for our documentation

## L
L- Write the deliverable n°1 |  |  | Not started
In progress
Achieve
DELIVERABLE 1 : Problem definition
Tâche L.1 | To write the context of the study ( 2 pages) | Link to return to the Gantt : | Gantt
Tâche L.2 | To write the problem statement (3 pages)
Tâche L.3 | To write the main objective of the project (2 pages)
Tâche L.4 | To make clear the final delivery
Tâche L.5 | To write the state of the art (5 pages)
Tâche L.6 | To write the workplan (1 page)
DELIVERABLE 2
DELIVERABLE 3
DELIVERABLE 4

## M
M- Press research phase |  |  | Not started
In progress
Achieve
Task M.1 | Analyze the compressor solutions on the market to make them as low tech as possible
Task M.2 | Look at what we can/want to keep from the existing compressor | Link to return to the Gantt : | Gantt
Task M.3 | Think about mechanical solutions (structures, compressor plates, compression system (car jack?, jack?) oven?, resistances in the plates?)
Task M.4 | Think about the electronics (temperature control, thermal wiring of resistors?)
Task M.5 | Think about the evacuation and filtration of toxic vapors/fumes
https://technology.plasticodyssey.org/presse-hydraulique-recyclage/

## N
N- Improvement of the press |  |  | Not started
In progress
Achieve
Tâche N.1 | Dismantle the prototype 'oven' and recover only the parts that interest us
Tâche N.2 | To make the engine support | Link to return to the Gantt : | Gantt
Tâche N.3 | Create the two heating plates system
Tâche N.4 | To install the electric part
Tâche N.5 | Secure the prototype if necessary to avoid burns
Tâche N.6 | Install the ventilation and air filtration system

## O
O- Calculation of costs |  |  | Not started
In progress
Achieve
SHREDDER
Tâche O.1 | Calculation of the estimated costs for the realisation of the shredder based on a low tech strategy | Link to return to the Gantt : | Gantt
Tâche O.2 | Document detailing the costs once the shredder prototype is completed
PRESS
Tâche O.3 | Calculation of the estimated costs for the realisation of the press based on a low tech strategy | Link to reach the shredder's cost :
Tâche O.4 | Document detailing the costs once the press prototype is completed | https://drive.google.com/drive/u/0/folders/1Usj1xGDWYTqddtzND61bQwhJWDBNp8lr
Link to reach the press's cost
https://drive.google.com/drive/u/0/folders/1pmRdCUKd53YlIkg1hb06DkIpRMV1LViT

## Ressources
Ressources used
First name | LAST NAME
Tom | BIANCIOTTO
Maxime | CLAVEL
Louis | GASTON
William | LEGARDEUR
Margaux | LENNE
Nsongurua Innocent | WILLIE