## Gantt
GANTT REV.3 |  | Durées | Ressources | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19
Open source plastic recycling machine |  |  |  | 20/09 - 26/09 | 27/09 - 03/10 | 04/10 - 10/10 | 11/10 - 17/10 | 18/10 - 24/10 | 25/10 - 31/10 | 01/11 - 07/11 | 08/11 - 14/11 | 15/11 - 21/11 | 22/11 - 28/11 | 29/11 - 05/12 | 06/12 - 12/12 | 13/12 - 19/12 | 20/12 - 26/12 | 27/12 - 02/01 | 03/01 - 07/01 | 10/01 - 14/01 | 17/01 - 21/01 | 24/01 - 28/01 | 31/01 - 04/02 | 07/02 - 11/02 | 14/02 - 18/02 | 21/02 - 25/02 | 28/02 - 06/03 | 07/03 - 13/03 | 14/03 - 20/03 | 21/03 - 27/03 | 28/03 - 03/04 | 04/04 - 10/04 | 11/04 - 17/04 | 18/04 - 24/05 | 25/04 - 29/05 | 02/05 - 06/05 | 09/05 - 13/05
Exam |  | NA | NA | S43: Exam 28/10; S44: TOUSSAINT; S45: Exam 8/11; S46: Exam 19/11; S51: NOEL; S52: NOEL; S3: PARTIELS S1; S4: !! REMANIEMENT ORGANISATION !!; S8: HIVER; S16: PAQUES
Deliverable |  |  |  | S46: L1 : 16 Novembre; S5: L2 : 1 Février; S11: L3 : 15 Mars; S15: L4 : mid may; S17: L5 : end may
A | Reading of technical documents | 2 | Team | bar: S38 to S39
B | Meeting/mail with Germain LEMASSON | 5 | Team | bar: S38; S47; S6; S12; S19
C | Project management | 3 | TB/ML | bar: S38 to S40
D | Systems Engineering | 7 | LG/MC/ML | bar: S39 to S43; S45; S9 to S10
E | Connecting the converter | 2 | ML/MC | bar: S39 to S40
F | Organisation of the collect/routing of plastic | 9 | Willie/ML | bar: S41 to S43; S45 to S50
G | Shredder supply chain | 8 | WNI/ML/MC | bar: S11 to S15; S17 to S19
H | Study of the current engine and the engines available | 3 | MC/ML | bar: S41 to S43
I | Improvement of the shredder | 21 | TB/WL/ML/MC | bar: S40 to S43; S45 to S50; S1 to S2; S5 to S7; S9 to S14
J | Tests | 7 | Team | bar: S50; S1 to S2; S15; S17 to S19
K | Write open source document on Github | 16 | Team | bar: S43; S50; S1 to S2; S5 to S7; S9 to S15; S17 to S19
L | Write the deliverables | 4 | Team | bar: S43; S45; S5; S10; S14 to S15
M | Hot press research phase | 6 | LG/MC | bar: S43; S45 to S50
N | Hot press state of the art | 7 | LG/TB/MC | bar: S12 to S15; S17 to S19
O | Calculation of costs | 7 | LG | bar: S41 to S42; S50; S1 to S2; S15; S17
Code couleur
Late
In time
Advance
Past
Revision date : 25/01/2022

## Feuille 20
GANTT REV.3 |  | Durées | Ressources | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19
Open source plastic recycling machine |  |  |  | 10/01 - 14/01 | 17/01 - 21/01 | 24/01 - 28/01 | 31/01 - 04/02 | 07/02 - 11/02 | 14/02 - 18/02 | 21/02 - 25/02 | 28/02 - 06/03 | 07/03 - 13/03 | 14/03 - 20/03 | 21/03 - 27/03 | 28/03 - 03/04 | 04/04 - 10/04 | 11/04 - 17/04 | 18/04 - 24/05 | 25/04 - 29/05 | 02/05 - 06/05 | 09/05 - 13/05
Exam |  | NA | NA | S3: PARTIELS S1; S4: !! REMANIEMENT ORGANISATION !!; S8: HIVER; S16: PAQUES
Deliverable |  |  |  | S5: L2 : 1 Février; S11: L3 : 15 Mars; S15: L4 : mid may; S17: L5 : end may
A | Reading of technical documents | 2 | Team
B | Meeting/mail with Germain LEMASSON | 5 | Team | bar: S6; S12; S19
C | Project management | 3 | TB/ML
D | Systems Engineering | 7 | LG/MC/ML | bar: S9 to S10
E | Connecting the converter | 2 | ML/MC
F | Organisation of the collect/routing of plastic | 9 | Willie/ML
G | Shredder supply chain | 8 | WNI/ML/MC | bar: S11 to S15; S17 to S19
H | Study of the current engine and the engines available | 3 | MC/ML
I | Improvement of the shredder | 21 | TB/WL/ML/MC | bar: S2; S5 to S7; S9 to S14
J | Tests | 7 | Team | bar: S2; S15; S17 to S19
K | Write open source document on Github | 16 | Team | bar: S2; S5 to S7; S9 to S15; S17 to S19
L | Write the deliverables | 4 | Team | bar: S5; S10; S14 to S15
M | Hot press research phase | 6 | LG/MC
N | Hot press state of the art | 7 | LG/TB/MC | bar: S12 to S15; S17 to S19
O | Calculation of costs | 7 | LG | bar: S2; S15; S17

## A
A- Reading of technical documents |  |  | Not started
In progress
Achieve
Tâche A.1 | Technical documentation
| - "Les différents types de plastique" | Link to return to the Gantt : | Gantt
- "Injection"
- "Guide pratique pour incorporer les matières plastiques recyclées"
- "Conception des pièces en plastique pour éviter les défauts géométriques"
Tâche A.2 | Documentation about the shredder
- "Motoréducteur Vassal"
- "Huike Heynau"
- "Condensateur motoréducteur"
- "Amélioration broyeur"
Tâche A.3 | Documentation about the compression of plastic
- "Test four V1"
- "Test four V2"
- "Amélioratioin compression"

## B
B- Meeting with Germain LEMASSON |  |  | Not started
In progress
Achieve
Tâche B.1 | First meeting with Mr LEMASSON (22/09/2021)
| - Presentation of himself and of the Fabmstic | Link to return to the Gantt : | Gantt
- Prensentation of the professional recycling tools
- His expectations
Tâche B.2 | Second meeting with Mr LEMASSON
- Show him our first progress
- To make clear the aim
- Speak about the communication tool
- Show him our objectives for the next few weeks
- Set a week for the next meeting
Tâche B.3 | Third meeting with Mr LEMASSON

## C
C- Project management |  |  | Not started
In progress
Achieve
Tâche C.1 | Make the project gantt chart
| - Write the tasks | Link to return to the Gantt : | Gantt
- Define the period of the tasks
- Allocate ressources
Tâche C.2 | Make the project risk analysis

## D
D- Systems Engineering |  |  | Not started
In progress
Achieve
SHREDDER
Tâche D.1 | Define the stakeholders | Link to return to the Gantt : | Gantt
Tâche D.2 | Define the services
Tâche D.3 | Define the logical architecture
Tâche D.4 | Make the requirements chart
Tâche D.5 | Put it on diagrams.net
PRESS
Tâche D.6 | Define the stakeholders
Tâche D.7 | Define the services
Tâche D.8 | Define the logical architecture
Tâche D.9 | Make the requirements chart
Tâche D.10 | Put it on diagrams.net

## E
E- Connecting the converter |  |  | Not started
In progress
Achieve
Tâche E.1 | Read the instruction manual of the converter
Tâche E.2 | To do the wirering | Link to return to the Gantt : | Gantt
Tâche E.3 | To test the motor in a basic case
Tâche E.4 | To solder the new buttons

## F
F- Organisation of the collect/routing of plastic |  |  |  | Not started
In progress
Achieve
Tâche F.1 | To organise the collect of ABS plastic in GI
| - To make a clear laminated notice showing the carton below and saying to throw away unused parts |  | Link to return to the Gantt : | Gantt
Tâche F.2 | To organise the collect of plastic with the RAFU network
| - To contact Germain LEMASSON to ask him his vision of things | Meeting : 24th of November
| - Start thinking about how to collect information and store it | Thanks to a google sheets
Tâche F.3 | To prepare the storage of [ABS/PLA/falling plastic sheet from the physiotherapist] ships
- To enquire about the storage of different types of plastic
Warning!! It should not have a dead center !!

## G
G- Shredder supply chain |  |  | Not started
In progress
Achieve
Tâche G.1 | Identify the source of the plastic to be shredded
Tâche G.2 | Identify clients | Link to return to the Gantt : | Gantt
Tâche G.3 | Identify the place where the chips are stored
Tâche G.4 | Identify packaging for transport + need for drying or not
Tâche G.5 | Transport: where, when, how
Tâche G.6 | Define a management interface for all this data

## H
H- Study of the current engine and the engines available |  |  | Not started
In progress
Achieve
Tâche H.1 | To calculate their torque
Tâche H.2 | To find others useful unformations | Link to return to the Gantt : | Gantt
Tâche H.3 | To make a comparative document
Tâche H.4 | To choose the most suitable engine

## I
I- Improvement of the shredder |  |  |  | Not started
In progress
Achieve
Tâche I.1 | To securise the shredder with a hopper
Tâche I.2 | To install a cover | The hinges and a wrist are missing | Link to return to the Gantt : | Gantt
Tâche I.3 | To install the electric part | connections to be made ; rail to be installated
Tâche I.4 | To prepare the electrical box | Water jet cutting machine
Tâche I.5 | To realise the housing (carter) | Draw in progress ; material : steel
Tâche I.6 | To make the engine support | Fixing only to wood may not be strong enough
Tâche I.7 | To design a bin (bac) for the big ships of plastic
Tâche I.8 | To make the bin | Water jet cutting machine

## J
J- Tests |  |  | Not started
In progress
Achieve
Tâche J.1 | To test a first time the shredder by shredding ABS/PLA/Physiotherapist plastic
Tâche J.2 | Do another test phase if the first one failed
Tâche J.3 | To contact la casemate in order to find a press and make test and do not wait until our press is ready | Link to return to the Gantt : | Gantt
Tâche J.4 | To make test in the Casemate
Contact pour la Casemate : Yoanna Nowicki
yoanna.nowicki@ccsti-grenoble.org

## K
K- Write all document (safety rules, working, ...) |  |  |  | Not started
In progress
Achieve
SHREDDER
Tâche K.1 | To write the safety rules of the shredder |  | Link to return to the Gantt : | Gantt
Tâche K.2 | To write a document about how to use the shredder
PRESS
Tâche K.3 | Discuss about possible safety rules of the hot press |  | Link given by Mr Boujut concerning open source document :
https://github.com/OPEN-NEXT/wp2.3_Guideline-for-documentation-of-OSH-design-reuse
Tâche K.5 | Think about which documents will be open source
- Dimensional calculations
- Drawings et CAD
- Assembly advice
- Wiring diagram
- Materials used
- Security documents
- Costs
Tâche K.6 | Open and set a git GitHub
Tâche K.7 | Write the thocumentation fofowing the Open source guidelines
Introduction
Specification
Design
Manufacturing
Assembly
Use
Maintenance
Disposal
Tâche K.8 | Find a licence for our documentation | GPL : License Public Générale

## L
L- Write the deliverable n°1 |  |  | Not started
In progress
Achieve
DELIVERABLE 1 : Problem definition
Tâche L.1 | To write the context of the study ( 2 pages) | Link to return to the Gantt : | Gantt
Tâche L.2 | To write the problem statement (3 pages)
Tâche L.3 | To write the main objective of the project (2 pages)
Tâche L.4 | To make clear the final delivery
Tâche L.5 | To write the state of the art (5 pages)
Tâche L.6 | To write the workplan (1 page)
DELIVERABLE 2
Tâche L.7 | To write the context of the study
Tâche L.8 | To write relevant (new) elements of State of the art
Tâche L.9 | To write current devlopments
Tâche L.10 | To write project task advancement
Tâche L.11 | To write project costs
Tâche L.12 | To write work plan
DELIVERABLE 3
DELIVERABLE 4

## M
M- Press research phase |  |  | Not started
In progress
Achieve
Task M.1 | Analyze the compressor solutions on the market to make them as low tech as possible
Task M.2 | Look at what we can/want to keep from the existing compressor | Link to return to the Gantt : | Gantt
Task M.3 | Make a first model
https://technology.plasticodyssey.org/presse-hydraulique-recyclage/

## N
N- Hot press state of the art |  |  | Not started
In progress
Achieve
Tâche N.1 | Define the components
Tâche N.2 | Define the sizing | Link to return to the Gantt : | Gantt
Tâche N.3 | Think about security
Tâche N.4 | Ventilation
Tâche N.5 | CAO
Describe and summarise the element of existing knowledge you already identified and that are necessary to frame your project

## O
O- Calculation of costs |  |  | Not started
In progress
Achieve
SHREDDER
Tâche O.1 | Calculation of the estimated costs for the realisation of the shredder based on a low tech strategy | Link to return to the Gantt : | Gantt
Tâche O.2 | Document detailing the costs once the shredder prototype is completed
PRESS
Tâche O.3 | Calculation of the estimated costs for the realisation of the press based on a low tech strategy | Link to reach the shredder's cost :
Tâche O.4 | Document detailing the costs once the press prototype is completed | https://drive.google.com/drive/u/0/folders/1Usj1xGDWYTqddtzND61bQwhJWDBNp8lr
Link to reach the press's cost
https://drive.google.com/drive/u/0/folders/1pmRdCUKd53YlIkg1hb06DkIpRMV1LViT

## Ressources
Ressources used |  |  | Ressoucres number | 6
First name | LAST NAME
Tom | BIANCIOTTO | TB
Maxime | CLAVEL | MC
Louis | GASTON | LG
William | LEGARDEUR | WL
Margaux | LENNE | ML
Nsongurua Innocent | WILLIE | WNI